## Slide 1: Project Management
Week1 Introduction

## Slide 2: This Week
Learning Outcomes of Module
Assessment Mechanism
Why Managers need Project Management (PM) Skills?
What is a Project?
Constraints of a Project
Why Projects Fail?
Local Mega Projects Success or Failure!
Current Mega Projects – World Perspective

## Slide 3: Learning Outcomes
1) Critically evaluate the nature of projects and the inter-relationship between time, cost and quality constraints
2) Critically evaluate the role of the project manager and the human resource elements of project management
3) Operate leading computer software tools to support project management activities
4) Evaluate and apply project support techniques including project optimization, control and trouble shooting
5) Apply the fundamental principles of planning budgeting, resourcing and risk management to a project based environment

## Slide 4: Assessment
Assignment based Case Study
4000 word report
Contains both written element and use of MS Project software
Assignment is usually confirmed around Week 4
Assignment Guidelines Week 5
Two Tutorials for Assignment Help- Nov 28th and Dec 5th 2011

## Slide 5: Why do managers need PM Skills
Traditionally most managers have not been involved in PM
Today project based organizations are becoming common i.e. organization are shifting away from conventional management hierarchy
Projects provide the means by which an organizations strategic plan can be achieved
Therefore, managers need to have PM skill in their armory

## Slide 6: Budget 2012 Projects
21st Century Policing Project
Seamless Education System Project
Music School in the Pan Yard Project
Art of Success Project
AUM 2 Project- estimated capital cost of US$1.9 billion
CariSal project- estimated cost of US$430 million

## Slide 7: Projects in Energy Sector 2012-2015 Investment US$ 5 Billion
The Reliance Bitumen Upgrader project
Methanol to Polypropylene project
Methanol to Acetic Acid project
Maleic Anhydride project
Melamine derivatives projects

## Slide 8: Typical projects in an organization
Developing Information Systems
Develop new products
Mergers and Acquisitions
Change in Structure
Rebranding
New locations
Constructing a new Building or facility

## Slide 9
‘ A project is whatever I call a project’

## Slide 10: What is a Project?
Projects are not ongoing operations
This means that a project is temporary
That is, it has a definite beginning and a definite end
The end is reached when the project’s objectives are achieved or when it becomes clear that they cannot be met or the project is no longer needed
Temporary does not mean short in duration

## Slide 11
Projects involve doing something novel
They are therefore produce an outcome which is unique
Uniqueness can be achieved even if the category to which it belongs is large e.g. New McDonald Location, HDC houses
Is a Healthy and Safety Inspection a Project?

## Slide 12: Definition
“Projects are unique, transient endeavours undertaken to achieve a desired outcome” APM (2004)
“A project is a temporary endeavour undertaken to create a unique product or service” PMI (2000)

## Slide 13: Further Characteristic
Progressive Elaboration:
  This integrates the concepts of temporary and unique
  Because the product is unique, the product must be progressively elaborated
  That is proceeding in steps, continuing steadily by increments
  The unique characteristics must be thoroughly and carefully worked out

## Slide 14
Uncertainty
  Again because of uniqueness the level certainty is low
  The future of cannot be predicted accurately
  Environmental conditions
  Emergent Properties- scope creep
  Uncertainty of cost of resources

## Slide 15: Project Constraints
You can have it cheap, you can have it right or you can have it quick. But you can only have two out of the three

## Slide 16: Refined Definition
“a unique set of coordinated activities, with definite starting and finishing points, undertaken by an individual or organization to meet specific performance objectives within defined schedule, cost and performance parameters”
British Standard 6079 (2000)

## Slide 17: Why Projects Fail?
Ready, fire, aim- shoot first whatever you hit is the target
It’s all in my head
We don’t have time to do this stuff
I’ve got certification, therefore I am a Project Mgr
We have a procedure for that
We need not use that methodology
We’ve done this before
No Planning

## Slide 18: Local Projects
Brian Lara Stadium
  Conceptualization Date: 2003
  Initial Estimated Cost: TT$ 850 Million, TT$ 250 M for Cricket Stadium
  Scope: Cricket stadium, the aquatic centre, cycling velodrome, football fields, gym, hotel accommodation
  Estimated Completion Date: Cricket World Cup 2007
  Main Project Issue: TT $125 million in advance payments to the project's main contractor despite the fact that the project was behind schedule
  Estimated Cost at Completion: TT $ 1.2 Billion
  Estimated Date of Completion: project scaled down to Cricket Stadium with no date insight

## Slide 19
Water Front Project
  Commencement: August 2005
  Scope: Two 26 Storey Office buildings, A 22 storey 428 room Hyatt Regency Hotel, largets conference room in Caribbean, 7 storey carpark 1200 vehicles
  Contract: Design Build to Bouygues Batiment
  Scheduled Open: 2008
  Actual Opening: April 2009
  Estimated Cost: TT$ 1.6 Billion
  Actual Cost: TT$ 3.4 Billion
  Funding: Loan, First Caribbean fixed interest rate of 6.09 per cent for 15.9 years

## Slide 20
NAPA
  Completion: Nov 2009
  Scope: 1500 seat hall, 2 practice halls, hotel, teaching rooms
  Estimated Cost: TT$ 500 Million
  Funding: 2% concessional loan from Republic of China for 20years
  Project Issue: Structural Defects TT$ 80 Million
  Contractor: Fixed Price, Design Build contract to Shanghai, but TT$ 100Million subcontracted to local contractors

## Slide 21: International Mega Projects
Expanding the Panama Canal
  In 2006, Panama’s voters endorsed a $5.25 billion plan to double the artificial river’s capacity by 2014
  Employing up to 40,000 construction workers
The World’s Longest Natural Gas Pipeline: The Trans-Afghanistan
  Transport gas from the shores of the Caspian Sea to the Indian Ocean
  The 56-inch pipeline, 1,040 miles stretching across Afghanistan will be one of the world’s longest and cost $7.6 billion

## Slide 22
The World’s Longest Tunnel: Gotthard Base Tunnel
  Railway tunnels under the Alps
  Will run more than 35 miles when it opens in 2018
  Construction on the €$6.4 billion project began in 2003
  More than 2,000 workers labor daily to make it a reality.
  Train station located 2,500 feet below the surface would include the world’s largest elevator

## Slide 23: The London Olympics 2012
Funded by LOCOG £ 2bn and Olympic Delivery Authority £7bn
The infrastructure includes an Energy Centre, Primary Substation and Pumping Station
The construction of all the new main venues and infrastructure for the London 2012 Games is now complete
Olympic could be show in 3D!! Video

## Slide 24: Useful Websites
Project Management Instititue- www.pmi.org
The Association for Project Management (UK)-www.apm.org.uk
Prince 2 2009- www.prince2.com
International Project Management Association- www.ipma.ch
Forum- www.gantthead.com